UNIVERSITY COMPLAINTS MANAGEMENT SYSTEM

PROJECT PLAN & REQUIREMENTS DOCUMENT

📋 TABLE OF CONTENTS

1. [Executive Summary](1-executive-summary)

2. [Project Overview](2-project-overview)

3. [Requirement Gathering Process](3-requirement-gathering-process)

4. [Stakeholder Analysis](4-stakeholder-analysis)

5. [Functional Requirements](5-functional-requirements)

6. [Non-Functional Requirements](6-non-functional-requirements)

7. [System Architecture](7-system-architecture)

8. [Database Design](8-database-design)

9. [User Roles & Permissions](9-user-roles--permissions)

10. [Feature Breakdown](10-feature-breakdown)

11. [Technology Stack](11-technology-stack)

12. [Development Phases & Timeline](12-development-phases--timeline)

13. [Risk Assessment](13-risk-assessment)

14. [Testing Plan](14-testing-plan)

15. [Deployment Plan](15-deployment-plan)

16. [Deliverables](16-deliverables)

17. [Budget Estimation](17-budget-estimation)

18. [Maintenance & Support](18-maintenance--support)

1. EXECUTIVE SUMMARY

1.1 Project Title

University Complaints & Request Management System (UCRMS)

1.2 Project Description

A comprehensive web-based software system designed for Nigerian universities to streamline the process of student complaint submission, administrative tracking, and resolution management. The system provides real-time analytics and reporting capabilities to identify bottlenecks and improve service delivery.

1.3 Project Objectives

| Objective | Description |

|-----------|-------------|

| Primary | Digitize and automate the complaint management process |

| Secondary | Reduce response time and improve student satisfaction |

| Tertiary | Provide data-driven insights for administrative decisions |

1.4 Expected Outcomes

✅ 70% reduction in complaint processing time

✅ 100% complaint tracking and accountability

✅ Zero lost or ignored complaints

✅ Real-time visibility into system performance

✅ Improved student-administration communication

1.5 Project Duration

8-10 Weeks (Estimated)

2. PROJECT OVERVIEW

2.1 Problem Statement

Nigerian university students currently face significant challenges when submitting complaints or requests to administration:

CURRENT PROBLEMS

❌ Manual paper-based complaint submission

❌ Long queues at administrative offices

❌ No tracking mechanism for submitted complaints

❌ Complaints get lost or ignored

❌ No accountability for response times

❌ Students unaware of complaint status

❌ No data to identify recurring issues

❌ Inefficient resource allocation

2.2 Proposed Solution

A web-based complaint management system that:

│                    PROPOSED SOLUTION                        │

│ ✅ Online complaint submission (24/7 access)                │

│ ✅ Automatic ticket generation and tracking                 │

│ ✅ Real-time status updates for students                    │

│ ✅ Admin dashboard for complaint management                 │

│ ✅ Priority-based complaint routing                         │

│ ✅ Analytics and reporting dashboard                        │

│ ✅ Email/SMS notifications                                  │

│ ✅ Performance metrics and KPIs                             │

2.3 Scope

In Scope ✅

| Module | Features |

|--------|----------|

| Student Portal | Registration, Login, Submit Complaints, Track Status, View History |

| Admin Portal | View All Complaints, Assign, Respond, Update Status, Manage Users |

| Super Admin | All Admin Features + System Configuration, User Management |

| Dashboard | Analytics, Charts, Reports, Export Data |

| Notifications | Email Notifications, In-App Notifications |

Out of Scope ❌

| Feature | Reason |

|---------|--------|

| Mobile App (Native) | Phase 2 consideration |

| SMS Notifications | Requires third-party integration (can add later) |

| Payment Integration | Not required for MVP |

| Multi-University Support | Single university focus for now |

| Offline Mode | Web-based system requires internet |

3. REQUIREMENT GATHERING PROCESS

3.1 Methodology

│              REQUIREMENT GATHERING PHASES                   │

├─────────────────────────────────────────────────────────────┤

│                                                             │

│   Phase 1: Stakeholder Identification                       │

│      ↓                                                      │

│   Phase 2: Interview & Survey                               │

│      ↓                                                      │

│   Phase 3: Document Analysis                                │

│      ↓                                                      │

│   Phase 4: Requirement Documentation                        │

│      ↓                                                      │

│   Phase 5: Validation & Sign-off                            │

3.2 Requirement Gathering Activities

Phase 1: Stakeholder Identification (Week 1 - Days 1-2)

| Activity | Description | Output |

|----------|-------------|--------|

| Identify key stakeholders | List all parties involved | Stakeholder Register |

| Classify stakeholders | Group by role and influence | Stakeholder Matrix |

| Establish communication | Set up meeting channels | Communication Plan |

Phase 2: Interviews & Surveys (Week 1 - Days 3-5)

| Stakeholder | Method | Questions Focus |

|-------------|--------|-----------------|

| Students | Online Survey | Pain points, desired features, usage patterns |

| Admin Staff | One-on-One Interview | Current workflow, challenges, requirements |

| IT Department | Technical Interview | Infrastructure, security, integration needs |

| Management | Executive Interview | Goals, KPIs, budget, timeline |

Sample Interview Questions:

```

FOR STUDENTS:

1. How do you currently submit complaints?

2. What are your biggest frustrations with the current process?

3. How long does it usually take to get a response?

4. What features would you find most helpful?

5. How would you prefer to receive status updates?

FOR ADMIN STAFF:

1. How many complaints do you handle daily/weekly?

2. What are the most common complaint types?

3. What information do you need to process a complaint?

4. What causes delays in resolving complaints?

5. What reports do you need for management?

FOR IT DEPARTMENT:

1. What is the current infrastructure?

2. What security requirements must be met?

3. Are there existing systems to integrate with?

4. What are the hosting preferences?

5. What are the backup and recovery requirements?

```

Phase 3: Document Analysis (Week 1 - Days 4-5)

| Document | Purpose |

|----------|---------|

| Current complaint forms | Understand required data fields |

| Process flowcharts | Map current workflow |

| Organizational structure | Understand reporting hierarchy |

| Previous system reports | Identify historical issues |

| University policies | Ensure compliance |

Phase 4: Requirement Documentation (Week 2 - Days 1-3)

| Deliverable | Description |

|-------------|-------------|

| Business Requirements Document (BRD) | High-level business needs |

| Functional Requirements Specification (FRS) | Detailed feature requirements |

| Non-Functional Requirements | Performance, security, usability |

| Use Case Diagrams | Visual user interactions |

| User Stories | Agile-format requirements |

Phase 5: Validation & Sign-off (Week 2 - Days 4-5)

| Activity | Participants | Output |

|----------|--------------|--------|

| Requirements Review Meeting | All stakeholders | Feedback Document |

| Requirement Prioritization | Client + Dev Team | Prioritized Backlog |

| Sign-off | Client/Project Sponsor | Approved Requirements |

---

4. STAKEHOLDER ANALYSIS

4.1 Stakeholder Register

| Stakeholder | Role | Interest Level | Influence | Engagement Strategy |

|-------------|------|----------------|-----------|---------------------|

| Students | End Users | High | Medium | Regular updates, feedback sessions |

| Admin Staff | End Users | High | High | Training, involvement in design |

| IT Department | Technical Support | Medium | High | Technical consultations |

| University Management | Sponsors | High | Very High | Executive reports, demos |

| Bursary Department | Data Consumer | Medium | Low | Report requirements |

| Academic Affairs | Data Consumer | Medium | Low | Report requirements |

4.2 Stakeholder Communication Matrix

```

┌──────────────────┬─────────────────┬──────────────┬────────────────┐

│   Stakeholder    │    Frequency    │    Method    │    Content     │

├──────────────────┼─────────────────┼──────────────┼────────────────┤

│ Management       │ Weekly          │ Email/Meet   │ Progress Report│

│ Admin Staff      │ Bi-weekly       │ Workshop     │ Demos/Feedback │

│ IT Department    │ As needed       │ Technical    │ Integration    │

│ Students         │ Monthly         │ Survey       │ Feedback       │

└──────────────────┴─────────────────┴──────────────┴────────────────┘

```

---

5. FUNCTIONAL REQUIREMENTS

5.1 User Management Module

FR-001: User Registration

| ID | FR-001 |

|----|--------|

| Title | Student Registration |

| Description | Students can create accounts using their university email and matric number |

| Priority | High |

| Acceptance Criteria | - Email must be valid university domain<br>- Matric number must be unique<br>- Password minimum 8 characters<br>- Email verification required |

FR-002: User Authentication

| ID | FR-002 |

|----|--------|

| Title | User Login |

| Description | Users can securely log into the system |

| Priority | High |

| Acceptance Criteria | - Support email/password login<br>- Session timeout after 24 hours<br>- Account lockout after 5 failed attempts<br>- Password reset via email |

FR-003: User Profile Management

| ID | FR-003 |

|----|--------|

| Title | Profile Management |

| Description | Users can view and update their profile information |

| Priority | Medium |

| Acceptance Criteria | - View profile details<br>- Update phone, department<br>- Change password<br>- Cannot change matric number |

5.2 Complaint Management Module

FR-004: Submit Complaint

| ID | FR-004 |

|----|--------|

| Title | Complaint Submission |

| Description | Students can submit new complaints/requests |

| Priority | High |

| Acceptance Criteria | - Select category from predefined list<br>- Enter title (max 200 chars)<br>- Enter description (unlimited)<br>- Attach files (optional, max 5MB each)<br>- Auto-generate ticket number<br>- Confirmation displayed |

FR-005: Track Complaint

| ID | FR-005 |

|----|--------|

| Title | Complaint Tracking |

| Description | Students can track status of submitted complaints |

| Priority | High |

| Acceptance Criteria | - View list of all submitted complaints<br>- Filter by status/category/date<br>- Search by ticket number<br>- View detailed complaint info<br>- See response history |

FR-006: Respond to Complaint

| ID | FR-006 |

|----|--------|

| Title | Add Response |

| Description | Students and admins can add responses to complaints |

| Priority | High |

| Acceptance Criteria | - Text response field<br>- Attach files<br>- Timestamp recorded<br>- Author name displayed |

5.3 Admin Management Module

FR-007: View All Complaints

| ID | FR-007 |

|----|--------|

| Title | Admin Complaint View |

| Description | Admins can view all complaints in the system |

| Priority | High |

| Acceptance Criteria | - List view with pagination<br>- Filter by status/category/date/priority<br>- Sort by any column<br>- Search functionality<br>- Export to CSV/PDF |

FR-008: Assign Complaint

| ID | FR-008 |

|----|--------|

| Title | Complaint Assignment |

| Description | Admins can assign complaints to specific staff members |

| Priority | Medium |

| Acceptance Criteria | - Select from list of admins<br>- Notify assigned admin<br>- Track assignment history |

FR-009: Update Complaint Status

| ID | FR-009 |

|----|--------|

| Title | Status Update |

| Description | Admins can update complaint status |

| Priority | High |

| Acceptance Criteria | - Status options: Pending, In Progress, Resolved, Closed, Rejected<br>- Require comment for status change<br>- Notify student of change<br>- Record timestamp |

FR-010: Set Priority

| ID | FR-010 |

|----|--------|

| Title | Priority Setting |

| Description | Admins can set/change complaint priority |

| Priority | Medium |

| Acceptance Criteria | - Priority levels: Low, Medium, High, Urgent<br>- Visual indicators for priority<br>- Sort by priority |

5.4 Dashboard & Reporting Module

FR-011: Admin Dashboard

| ID | FR-011 |

|----|--------|

| Title | Analytics Dashboard |

| Description | Visual dashboard showing key metrics |

| Priority | High |

| Acceptance Criteria | - Total complaints count<br>- Status distribution chart<br>- Category distribution<br>- Average resolution time<br>- Trend over time<br>- Recent complaints list |

FR-012: Generate Reports

| ID | FR-012 |

|----|--------|

| Title | Report Generation |

| Description | Generate various reports for management |

| Priority | Medium |

| Acceptance Criteria | - Date range selection<br>- Filter by category/status<br>- Export to PDF/Excel<br>- Include charts and tables |

FR-013: Student Dashboard

| ID | FR-013 |

|----|--------|

| Title | Student Dashboard |

| Description | Personal dashboard for students |

| Priority | Medium |

| Acceptance Criteria | - My complaints summary<br>- Status breakdown<br>- Recent activity<br>- Quick submit button |

5.5 Notification Module

FR-014: Email Notifications

| ID | FR-014 |

|----|--------|

| Title | Email Alerts |

| Description | Automated email notifications for key events |

| Priority | Medium |

| Acceptance Criteria | - New complaint confirmation<br>- Status change notification<br>- New response notification<br>- Assignment notification |

FR-015: In-App Notifications

| ID | FR-015 |

|----|--------|

| Title | System Notifications |

| Description | In-app notification system |

| Priority | Low |

| Acceptance Criteria | - Notification bell icon<br>- Unread count badge<br>- Mark as read<br>- Notification history |

5.6 User Stories Summary

```

┌────────────────────────────────────────────────────────────────────┐

│                        USER STORIES                                │

├────────────────────────────────────────────────────────────────────┤

│                                                                    │

│ STUDENT USER STORIES:                                              │

│                                                                    │

│ US-001: As a student, I want to register an account so that I     │

│         can access the complaint system.                           │

│                                                                    │

│ US-002: As a student, I want to log in securely so that my        │

│         information is protected.                                  │

│                                                                    │

│ US-003: As a student, I want to submit a complaint so that my     │

│         issue can be addressed.                                    │

│                                                                    │

│ US-004: As a student, I want to track my complaint status so      │

│         that I know if it's being handled.                         │

│                                                                    │

│ US-005: As a student, I want to receive notifications so that     │

│         I'm updated on my complaint progress.                      │

│                                                                    │

│ US-006: As a student, I want to view my complaint history so      │

│         that I can reference past issues.                          │

│                                                                    │

│ US-007: As a student, I want to add additional information to     │

│         my complaint so that I can provide more context.           │

│                                                                    │

├────────────────────────────────────────────────────────────────────┤

│                                                                    │

│ ADMIN USER STORIES:                                                │

│                                                                    │

│ US-008: As an admin, I want to view all complaints so that I      │

│         can manage them effectively.                               │

│                                                                    │

│ US-009: As an admin, I want to filter complaints so that I can    │

│         find specific issues quickly.                              │

│                                                                    │

│ US-010: As an admin, I want to update complaint status so that    │

│         students are informed of progress.                         │

│                                                                    │

│ US-011: As an admin, I want to respond to complaints so that I    │

│         can communicate with students.                             │

│                                                                    │

│ US-012: As an admin, I want to assign complaints so that the      │

│         right department handles them.                             │

│                                                                    │

│ US-013: As an admin, I want to view analytics so that I can       │

│         identify trends and issues.                                │

│                                                                    │

│ US-014: As an admin, I want to generate reports so that I can     │

│         present data to management.                                │

│                                                                    │

├────────────────────────────────────────────────────────────────────┤

│                                                                    │

│ SUPER ADMIN USER STORIES:                                          │

│                                                                    │

│ US-015: As a super admin, I want to manage user accounts so       │

│         that I control system access.                              │

│                                                                    │

│ US-016: As a super admin, I want to configure categories so       │

│         that the system fits our needs.                            │

│                                                                    │

│ US-017: As a super admin, I want to view system-wide analytics    │

│         so that I can make informed decisions.                     │

│                                                                    │

└────────────────────────────────────────────────────────────────────┘

```

---

6. NON-FUNCTIONAL REQUIREMENTS

6.1 Performance Requirements

| ID | Requirement | Target |

|----|-------------|--------|

| NFR-001 | Page Load Time | < 3 seconds |

| NFR-002 | API Response Time | < 500ms |

| NFR-003 | Concurrent Users | Support 500+ simultaneous users |

| NFR-004 | Database Queries | Optimized with indexing |

| NFR-005 | File Upload | Max 5MB per file, 10MB total |

6.2 Security Requirements

| ID | Requirement | Implementation |

|----|-------------|----------------|

| NFR-006 | Password Encryption | Bcrypt hashing algorithm |

| NFR-007 | Data Transmission | HTTPS/TLS encryption |

| NFR-008 | Authentication | JWT tokens with expiration |

| NFR-009 | Authorization | Role-based access control (RBAC) |

| NFR-010 | Input Validation | Server-side validation, SQL injection prevention |

| NFR-011 | Session Management | Secure session handling, timeout |

| NFR-012 | Audit Logging | Log all sensitive operations |

6.3 Usability Requirements

| ID | Requirement | Description |

|----|-------------|-------------|

| NFR-013 | Responsive Design | Works on desktop, tablet, mobile |

| NFR-014 | Browser Compatibility | Chrome, Firefox, Safari, Edge |

| NFR-015 | Accessibility | WCAG 2.1 Level AA compliance |

| NFR-016 | Language | English (Nigerian context) |

| NFR-017 | Learning Curve | Users productive within 30 minutes |

6.4 Reliability Requirements

| ID | Requirement | Target |

|----|-------------|--------|

| NFR-018 | System Uptime | 99.5% availability |

| NFR-019 | Data Backup | Daily automated backups |

| NFR-020 | Recovery Time | < 4 hours for disaster recovery |

| NFR-021 | Error Handling | Graceful error messages |

6.5 Scalability Requirements

| ID | Requirement | Description |

|----|-------------|-------------|

| NFR-022 | User Growth | Scale to 10,000+ registered users |

| NFR-023 | Data Growth | Handle 50,000+ complaints |

| NFR-024 | Horizontal Scaling | Support load balancing |

---

7. SYSTEM ARCHITECTURE

7.1 High-Level Architecture

```

┌─────────────────────────────────────────────────────────────────────┐

│                        SYSTEM ARCHITECTURE                          │

└─────────────────────────────────────────────────────────────────────┘

┌─────────────┐

│   USERS     │

│             │

│ ┌─────────┐ │

│ │Students │ │

│ └─────────┘ │

│ ┌─────────┐ │

│ │ Admins  │ │

│ └─────────┘ │

└──────┬──────┘

│

│ HTTPS

▼

┌───────────────────────┐

│     LOAD BALANCER     │

│       (Nginx)         │

└───────────┬───────────┘

│

┌──────────────────────┼──────────────────────┐

│                      │                      │

▼                      ▼                      ▼

┌─────────────────┐   ┌─────────────────┐   ┌─────────────────┐

│   FRONTEND      │   │   FRONTEND      │   │   FRONTEND      │

│   (React.js)    │   │   (React.js)    │   │   (React.js)    │

│   Static Files  │   │   Static Files  │   │   Static Files  │

└────────┬────────┘   └────────┬────────┘   └────────┬────────┘

│                      │                      │

└──────────────────────┼──────────────────────┘

│

│ REST API

▼

┌───────────────────────┐

│    API GATEWAY        │

│                       │

└───────────┬───────────┘

│

┌──────────────────────┼──────────────────────┐

│                      │                      │

▼                      ▼                      ▼

┌─────────────────┐   ┌─────────────────┐   ┌─────────────────┐

│   BACKEND       │   │   BACKEND       │   │   BACKEND       │

│   (Flask)       │   │   (Flask)       │   │   (Flask)       │

│   REST API      │   │   REST API      │   │   REST API      │

└────────┬────────┘   └────────┬────────┘   └────────┬────────┘

│                      │                      │

└──────────────────────┼──────────────────────┘

│

┌────────────────┼────────────────┐

│                │                │

▼                ▼                ▼

┌─────────────┐   ┌─────────────┐   ┌─────────────┐

│  DATABASE   │   │   CACHE     │   │   FILE      │

│ PostgreSQL  │   │   Redis     │   │  STORAGE    │

│             │   │             │   │             │

└─────────────┘   └─────────────┘   └─────────────┘

```

7.2 Component Architecture

```

┌─────────────────────────────────────────────────────────────────────┐

│                      COMPONENT ARCHITECTURE                         │

└─────────────────────────────────────────────────────────────────────┘

┌─────────────────────────────────────────────────────────────────────┐

│                         PRESENTATION LAYER                          │

│                          (React.js + Tailwind CSS)                  │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│  ┌──────────────┐  ┌──────────────┐  ┌──────────────┐              │

│  │   Auth       │  │   Student    │  │    Admin     │              │

│  │   Pages      │  │   Portal     │  │   Portal     │              │

│  │              │  │              │  │              │              │

│  │ - Login      │  │ - Dashboard  │  │ - Dashboard  │              │

│  │ - Register   │  │ - Submit     │  │ - Complaints │              │

│  │ - Forgot PW  │  │ - Track      │  │ - Users      │              │

│  │              │  │ - History    │  │ - Reports    │              │

│  └──────────────┘  └──────────────┘  └──────────────┘              │

│                                                                     │

│  ┌─────────────────────────────────────────────────────────────┐   │

│  │                    SHARED COMPONENTS                         │   │

│  │  Navbar | Sidebar | Cards | Tables | Charts | Forms | Modal │   │

│  └─────────────────────────────────────────────────────────────┘   │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

│

│ HTTP/REST

▼

┌─────────────────────────────────────────────────────────────────────┐

│                         APPLICATION LAYER                           │

│                            (Flask REST API)                         │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│  ┌──────────────┐  ┌──────────────┐  ┌──────────────┐              │

│  │    Auth      │  │  Complaint   │  │  Dashboard   │              │

│  │   Routes     │  │   Routes     │  │   Routes     │              │

│  │              │  │              │  │              │              │

│  │ /api/auth/ │  │ /api/student │  │ /api/dashboard│              │

│  │              │  │ /api/admin   │  │              │              │

│  └──────────────┘  └──────────────┘  └──────────────┘              │

│                                                                     │

│  ┌─────────────────────────────────────────────────────────────┐   │

│  │                      MIDDLEWARE                              │   │

│  │  JWT Auth | CORS | Rate Limiting | Error Handling | Logging │   │

│  └─────────────────────────────────────────────────────────────┘   │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

│

▼

┌─────────────────────────────────────────────────────────────────────┐

│                           DATA LAYER                                │

│                      (SQLAlchemy ORM + PostgreSQL)                  │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│  ┌──────────────┐  ┌──────────────┐  ┌──────────────┐              │

│  │    User      │  │  Complaint   │  │   Response   │              │

│  │   Model      │  │    Model     │  │    Model     │              │

│  └──────────────┘  └──────────────┘  └──────────────┘              │

│                                                                     │

│  ┌──────────────┐  ┌──────────────┐                                │

│  │ Notification │  │    Audit     │                                │

│  │    Model     │  │     Log      │                                │

│  └──────────────┘  └──────────────┘                                │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

```

7.3 API Architecture

```

┌─────────────────────────────────────────────────────────────────────┐

│                         API ENDPOINTS                               │

└─────────────────────────────────────────────────────────────────────┘

BASE URL: https://api.university-complaints.com/api/v1

┌─────────────────────────────────────────────────────────────────────┐

│ AUTHENTICATION                                                      │

├─────────────────────────────────────────────────────────────────────┤

│ POST   /auth/register          Register new student                 │

│ POST   /auth/login             Login user                           │

│ POST   /auth/logout            Logout user                          │

│ POST   /auth/refresh           Refresh access token                 │

│ GET    /auth/me                Get current user                     │

│ POST   /auth/forgot-password   Request password reset               │

│ POST   /auth/reset-password    Reset password                       │

│ POST   /auth/change-password   Change password                      │

└─────────────────────────────────────────────────────────────────────┘

┌─────────────────────────────────────────────────────────────────────┐

│ STUDENT ENDPOINTS                                                   │

├─────────────────────────────────────────────────────────────────────┤

│ GET    /student/complaints          Get my complaints               │

│ POST   /student/complaints          Create new complaint            │

│ GET    /student/complaints/:id      Get complaint details           │

│ POST   /student/complaints/:id/respond   Add response               │

│ GET    /student/stats               Get my statistics               │

│ GET    /student/profile             Get my profile                  │

│ PUT    /student/profile             Update my profile               │

└─────────────────────────────────────────────────────────────────────┘

┌─────────────────────────────────────────────────────────────────────┐

│ ADMIN ENDPOINTS                                                     │

├─────────────────────────────────────────────────────────────────────┤

│ GET    /admin/complaints            Get all complaints              │

│ GET    /admin/complaints/:id        Get complaint details           │

│ PUT    /admin/complaints/:id        Update complaint                │

│ PUT    /admin/complaints/:id/status Update status                   │

│ PUT    /admin/complaints/:id/assign Assign complaint                │

│ POST   /admin/complaints/:id/respond Add response                   │

│ GET    /admin/users                 Get all users                   │

│ POST   /admin/users                 Create admin user               │

│ PUT    /admin/users/:id             Update user                     │

│ DELETE /admin/users/:id             Deactivate user                 │

└─────────────────────────────────────────────────────────────────────┘

┌─────────────────────────────────────────────────────────────────────┐

│ DASHBOARD ENDPOINTS                                                 │

├─────────────────────────────────────────────────────────────────────┤

│ GET    /dashboard/stats             Get overview statistics         │

│ GET    /dashboard/charts/status     Status distribution             │

│ GET    /dashboard/charts/category   Category distribution           │

│ GET    /dashboard/charts/trend      Complaints over time            │

│ GET    /dashboard/reports           Generate reports                │

│ GET    /dashboard/export            Export data                     │

└─────────────────────────────────────────────────────────────────────┘

┌─────────────────────────────────────────────────────────────────────┐

│ UTILITY ENDPOINTS                                                   │

├─────────────────────────────────────────────────────────────────────┤

│ GET    /categories                  Get complaint categories        │

│ GET    /departments                 Get departments list            │

│ GET    /faculties                   Get faculties list              │

│ POST   /upload                      Upload file attachment          │

└─────────────────────────────────────────────────────────────────────┘

```

---

8. DATABASE DESIGN

8.1 Entity Relationship Diagram (ERD)

```

┌─────────────────────────────────────────────────────────────────────┐

│                    ENTITY RELATIONSHIP DIAGRAM                      │

└─────────────────────────────────────────────────────────────────────┘

┌─────────────────┐       ┌─────────────────┐       ┌─────────────────┐

│     USERS       │       │   COMPLAINTS    │       │   RESPONSES     │

├─────────────────┤       ├─────────────────┤       ├─────────────────┤

│ PK id           │───┐   │ PK id           │───┐   │ PK id           │

│    email        │   │   │ FK user_id      │◄──┘   │ FK complaint_id │◄──┐

│    password_hash│   │   │ FK assigned_to  │◄──┐   │ FK user_id      │◄──┤

│    full_name    │   │   │    ticket_number│   │   │    message      │   │

│    matric_number│   │   │    category     │   │   │    is_internal  │   │

│    department   │   │   │    title        │   │   │    created_at   │   │

│    faculty      │   └──►│    description  │   │   └─────────────────┘   │

│    phone        │       │    status       │   │                         │

│    role         │       │    priority     │   │   ┌─────────────────┐   │

│    is_active    │       │    attachments  │   │   │  NOTIFICATIONS  │   │

│    created_at   │───────│    created_at   │   │   ├─────────────────┤   │

│    updated_at   │       │    updated_at   │   │   │ PK id           │   │

└─────────────────┘       │    resolved_at  │   │   │ FK user_id      │◄──┤

└─────────────────┘   │   │ FK complaint_id │◄──┤

│   │    type         │   │

┌─────────────────┐       ┌─────────────────┐   │   │    message      │   │

│   DEPARTMENTS   │       │   CATEGORIES    │   │   │    is_read      │   │

├─────────────────┤       ├─────────────────┤   │   │    created_at   │   │

│ PK id           │       │ PK id           │   │   └─────────────────┘   │

│    name         │       │    name         │   │                         │

│    faculty_id   │       │    description  │   │   ┌─────────────────┐   │

│    created_at   │       │    is_active    │   │   │   AUDIT_LOGS    │   │

└─────────────────┘       └─────────────────┘   │   ├─────────────────┤   │

│   │ PK id           │   │

┌─────────────────┐                             │   │ FK user_id      │◄──┘

│    FACULTIES    │                             │   │    action       │

├─────────────────┤                             │   │    entity_type  │

│ PK id           │                             │   │    entity_id    │

│    name         │                             │   │    old_values   │

│    created_at   │◄────────────────────────────┘   │    new_values   │

└─────────────────┘                                 │    ip_address   │

│    created_at   │

└─────────────────┘

```

8.2 Table Definitions

Users Table

```sql

CREATE TABLE users (

id              SERIAL PRIMARY KEY,

email           VARCHAR(120) UNIQUE NOT NULL,

password_hash   VARCHAR(255) NOT NULL,

full_name       VARCHAR(100) NOT NULL,

matric_number   VARCHAR(20) UNIQUE,

department      VARCHAR(100),

faculty         VARCHAR(100),

phone           VARCHAR(20),

role            VARCHAR(20) DEFAULT 'student',

is_active       BOOLEAN DEFAULT TRUE,

created_at      TIMESTAMP DEFAULT CURRENT_TIMESTAMP,

updated_at      TIMESTAMP DEFAULT CURRENT_TIMESTAMP

);

CREATE INDEX idx_users_email ON users(email);

CREATE INDEX idx_users_matric ON users(matric_number);

CREATE INDEX idx_users_role ON users(role);

```

Complaints Table

```sql

CREATE TABLE complaints (

id              SERIAL PRIMARY KEY,

ticket_number   VARCHAR(20) UNIQUE NOT NULL,

user_id         INTEGER REFERENCES users(id),

category        VARCHAR(50) NOT NULL,

title           VARCHAR(200) NOT NULL,

description     TEXT NOT NULL,

status          VARCHAR(20) DEFAULT 'pending',

priority        VARCHAR(20) DEFAULT 'medium',

assigned_to     INTEGER REFERENCES users(id),

attachments     JSONB DEFAULT '[]',

created_at      TIMESTAMP DEFAULT CURRENT_TIMESTAMP,

updated_at      TIMESTAMP DEFAULT CURRENT_TIMESTAMP,

resolved_at     TIMESTAMP

);

CREATE INDEX idx_complaints_ticket ON complaints(ticket_number);

CREATE INDEX idx_complaints_user ON complaints(user_id);

CREATE INDEX idx_complaints_status ON complaints(status);

CREATE INDEX idx_complaints_category ON complaints(category);

CREATE INDEX idx_complaints_created ON complaints(created_at);

```

Responses Table

```sql

CREATE TABLE responses (

id              SERIAL PRIMARY KEY,

complaint_id    INTEGER REFERENCES complaints(id) ON DELETE CASCADE,

user_id         INTEGER REFERENCES users(id),

message         TEXT NOT NULL,

is_internal     BOOLEAN DEFAULT FALSE,

created_at      TIMESTAMP DEFAULT CURRENT_TIMESTAMP

);

CREATE INDEX idx_responses_complaint ON responses(complaint_id);

```

Notifications Table

```sql

CREATE TABLE notifications (

id              SERIAL PRIMARY KEY,

user_id         INTEGER REFERENCES users(id),

complaint_id    INTEGER REFERENCES complaints(id),

type            VARCHAR(50) NOT NULL,

message         TEXT NOT NULL,

is_read         BOOLEAN DEFAULT FALSE,

created_at      TIMESTAMP DEFAULT CURRENT_TIMESTAMP

);

CREATE INDEX idx_notifications_user ON notifications(user_id);

CREATE INDEX idx_notifications_read ON notifications(is_read);

```

---

9. USER ROLES & PERMISSIONS

9.1 Role Definitions

```

┌─────────────────────────────────────────────────────────────────────┐

│                         USER ROLES                                  │

└─────────────────────────────────────────────────────────────────────┘

┌──────────────┬──────────────────────────────────────────────────────┐

│    ROLE      │                    DESCRIPTION                       │

├──────────────┼──────────────────────────────────────────────────────┤

│   Student    │ Regular university student who can submit and track  │

│              │ complaints. Limited to their own data only.          │

├──────────────┼──────────────────────────────────────────────────────┤

│   Admin      │ Administrative staff who can view, manage, and       │

│              │ respond to all complaints. Can view reports.         │

├──────────────┼──────────────────────────────────────────────────────┤

│ Super Admin  │ System administrator with full access including      │

│              │ user management and system configuration.            │

└──────────────┴──────────────────────────────────────────────────────┘

```

9.2 Permission Matrix

```

┌─────────────────────────────────────────────────────────────────────┐

│                      PERMISSION MATRIX                              │

└─────────────────────────────────────────────────────────────────────┘

┌─────────────────────────────┬─────────┬─────────┬─────────────┐

│         PERMISSION          │ STUDENT │  ADMIN  │ SUPER ADMIN │

├─────────────────────────────┼─────────┼─────────┼─────────────┤

│ Register Account            │    ✅    │    ❌    │      ❌      │

│ Login/Logout                │    ✅    │    ✅    │      ✅      │

│ Update Own Profile          │    ✅    │    ✅    │      ✅      │

├─────────────────────────────┼─────────┼─────────┼─────────────┤

│ Submit Complaint            │    ✅    │    ❌    │      ❌      │

│ View Own Complaints         │    ✅    │    ✅    │      ✅      │

│ View All Complaints         │    ❌    │    ✅    │      ✅      │

│ Respond to Own Complaint    │    ✅    │    ✅    │      ✅      │

│ Respond to Any Complaint    │    ❌    │    ✅    │      ✅      │

├─────────────────────────────┼─────────┼─────────┼─────────────┤

│ Update Complaint Status     │    ❌    │    ✅    │      ✅      │

│ Assign Complaint            │    ❌    │    ✅    │      ✅      │

│ Set Complaint Priority      │    ❌    │    ✅    │      ✅      │

│ Delete Complaint            │    ❌    │    ❌    │      ✅      │

├─────────────────────────────┼─────────┼─────────┼─────────────┤

│ View Own Dashboard          │    ✅    │    ✅    │      ✅      │

│ View Admin Dashboard        │    ❌    │    ✅    │      ✅      │

│ View Analytics              │    ❌    │    ✅    │      ✅      │

│ Generate Reports            │    ❌    │    ✅    │      ✅      │

│ Export Data                 │    ❌    │    ✅    │      ✅      │

├─────────────────────────────┼─────────┼─────────┼─────────────┤

│ View Users List             │    ❌    │    ❌    │      ✅      │

│ Create Admin User           │    ❌    │    ❌    │      ✅      │

│ Deactivate User             │    ❌    │    ❌    │      ✅      │

│ System Configuration        │    ❌    │    ❌    │      ✅      │

│ View Audit Logs             │    ❌    │    ❌    │      ✅      │

└─────────────────────────────┴─────────┴─────────┴─────────────┘

```

---

10. FEATURE BREAKDOWN

10.1 Module Feature Matrix

```

┌─────────────────────────────────────────────────────────────────────┐

│                      FEATURE BREAKDOWN                              │

└─────────────────────────────────────────────────────────────────────┘

MODULE 1: AUTHENTICATION & USER MANAGEMENT

├── User Registration (Students)

│   ├── Email validation

│   ├── Password strength requirements

│   ├── Matric number validation

│   └── Email verification

├── User Login

│   ├── Email/Password authentication

│   ├── JWT token generation

│   ├── Remember me option

│   └── Account lockout protection

├── Password Management

│   ├── Forgot password

│   ├── Reset password via email

│   └── Change password

└── Profile Management

├── View profile

├── Edit profile

└── Profile picture upload

MODULE 2: STUDENT COMPLAINT PORTAL

├── Dashboard

│   ├── Summary statistics

│   ├── Recent complaints

│   ├── Quick actions

│   └── Notifications

├── Submit Complaint

│   ├── Category selection

│   ├── Title and description

│   ├── Priority selection

│   ├── File attachments

│   └── Submission confirmation

├── Track Complaints

│   ├── List view with filters

│   ├── Search by ticket number

│   ├── Status indicators

│   └── Timeline view

└── Complaint Details

├── Full complaint info

├── Response history

├── Add response

└── Download attachments

MODULE 3: ADMIN MANAGEMENT PORTAL

├── Dashboard

│   ├── KPI cards

│   ├── Status distribution chart

│   ├── Category breakdown

│   ├── Recent activity

│   └── Pending actions

├── Complaint Management

│   ├── View all complaints

│   ├── Advanced filtering

│   ├── Bulk actions

│   ├── Update status

│   ├── Assign to staff

│   ├── Set priority

│   └── Add internal notes

├── User Management (Super Admin)

│   ├── View all users

│   ├── Create admin accounts

│   ├── Activate/Deactivate users

│   └── Reset user passwords

└── Reports & Analytics

├── Overview statistics

├── Trend analysis

├── Category analysis

├── Response time analysis

├── Staff performance

└── Export to PDF/Excel

MODULE 4: NOTIFICATION SYSTEM

├── Email Notifications

│   ├── New complaint confirmation

│   ├── Status change alerts

│   ├── Response notifications

│   └── Assignment notifications

└── In-App Notifications

├── Real-time updates

├── Notification center

├── Mark as read

└── Notification preferences

MODULE 5: REPORTING & ANALYTICS

├── Dashboard Widgets

│   ├── Total complaints chart

│   ├── Status breakdown pie chart

│   ├── Category bar chart

│   ├── Monthly trend line chart

│   └── Average resolution time

├── Report Generation

│   ├── Custom date ranges

│   ├── Filter by category/status

│   ├── PDF export

│   └── Excel export

└── Performance Metrics

├── Response time tracking

├── Resolution rate

└── Staff workload analysis

```

---

11. TECHNOLOGY STACK

11.1 Technology Overview

```

┌─────────────────────────────────────────────────────────────────────┐

│                      TECHNOLOGY STACK                               │

└─────────────────────────────────────────────────────────────────────┘

┌─────────────────┬───────────────────────────────────────────────────┐

│     LAYER       │                   TECHNOLOGY                      │

├─────────────────┼───────────────────────────────────────────────────┤

│                 │                                                   │

│   FRONTEND      │  React.js 18.x                                    │

│                 │  ├── React Router v6 (Navigation)                 │

│                 │  ├── Axios (HTTP Client)                          │

│                 │  ├── React Query (Data Fetching)                  │

│                 │  ├── Zustand/Context API (State Management)       │

│                 │  ├── React Hook Form (Form Handling)              │

│                 │  └── Chart.js / Recharts (Charts)                 │

│                 │                                                   │

│   STYLING       │  Tailwind CSS 3.x                                 │

│                 │  ├── Headless UI (Components)                     │

│                 │  ├── Heroicons (Icons)                            │

│                 │  └── Custom Design System                         │

│                 │                                                   │

├─────────────────┼───────────────────────────────────────────────────┤

│                 │                                                   │

│   BACKEND       │  Python 3.11+ / Flask 3.x                         │

│                 │  ├── Flask-SQLAlchemy (ORM)                       │

│                 │  ├── Flask-Migrate (DB Migrations)                │

│                 │  ├── Flask-JWT-Extended (Authentication)          │

│                 │  ├── Flask-CORS (Cross-Origin)                    │

│                 │  ├── Flask-Bcrypt (Password Hashing)              │

│                 │  ├── Flask-Mail (Email)                           │

│                 │  └── Marshmallow (Serialization)                  │

│                 │                                                   │

├─────────────────┼───────────────────────────────────────────────────┤

│                 │                                                   │

│   DATABASE      │  PostgreSQL 15.x (Production)                     │

│                 │  SQLite (Development)                             │

│                 │  Redis (Caching - Optional)                       │

│                 │                                                   │

├─────────────────┼───────────────────────────────────────────────────┤

│                 │                                                   │

│   DEPLOYMENT    │  Option 1: DigitalOcean Droplet                   │

│                 │  Option 2: AWS EC2 + RDS                          │

│                 │  Option 3: Heroku + Render                        │

│                 │                                                   │

│   WEB SERVER    │  Nginx (Reverse Proxy)                            │

│                 │  Gunicorn (WSGI Server)                           │

│                 │                                                   │

├─────────────────┼───────────────────────────────────────────────────┤

│                 │                                                   │

│   DEV TOOLS     │  Git + GitHub (Version Control)                   │

│                 │  VS Code (IDE)                                    │

│                 │  Postman (API Testing)                            │

│                 │  Docker (Containerization - Optional)             │

│                 │                                                   │

└─────────────────┴───────────────────────────────────────────────────┘

```

11.2 Package Dependencies

Backend (requirements.txt)

```

Core Flask

Flask==3.0.0

Flask-SQLAlchemy==3.1.1

Flask-Migrate==4.0.5

Flask-JWT-Extended==4.6.0

Flask-CORS==4.0.0

Flask-Bcrypt==1.0.1

Flask-Mail==0.9.1

Database

psycopg2-binary==2.9.9

SQLAlchemy==2.0.23

Utilities

python-dotenv==1.0.0

marshmallow==3.20.1

email-validator==2.1.0

Pillow==10.1.0

Production

gunicorn==21.2.0

Development

pytest==7.4.3

pytest-cov==4.1.0

black==23.11.0

flake8==6.1.0

```

Frontend (package.json)

```json

{

"dependencies": {

"react": "^18.2.0",

"react-dom": "^18.2.0",

"react-router-dom": "^6.20.0",

"axios": "^1.6.2",

"@tanstack/react-query": "^5.8.4",

"react-hook-form": "^7.48.2",

"recharts": "^2.10.3",

"date-fns": "^2.30.0",

"@headlessui/react": "^1.7.17",

"@heroicons/react": "^2.0.18",

"react-hot-toast": "^2.4.1",

"zustand": "^4.4.7"

},

"devDependencies": {

"tailwindcss": "^3.3.5",

"autoprefixer": "^10.4.16",

"postcss": "^8.4.31",

"vite": "^5.0.0",

"@vitejs/plugin-react": "^4.2.0",

"eslint": "^8.54.0",

"prettier": "^3.1.0"

}

}

```

---

12. DEVELOPMENT PHASES & TIMELINE

12.1 Project Timeline Overview

```

┌─────────────────────────────────────────────────────────────────────┐

│                    PROJECT TIMELINE (10 WEEKS)                      │

└─────────────────────────────────────────────────────────────────────┘

Week 1-2    ████████████████████                    Planning & Setup

Week 3-4    ████████████████████                    Authentication

Week 5-6    ████████████████████                    Student Portal

Week 7-8    ████████████████████                    Admin Portal

Week 9      ██████████                              Dashboard & Reports

Week 10     ██████████                              Testing & Deployment

┌─────────────────────────────────────────────────────────────────────┐

│ GANTT CHART                                                         │

├──────┬──────┬──────┬──────┬──────┬──────┬──────┬──────┬──────┬──────┤

│ Wk 1 │ Wk 2 │ Wk 3 │ Wk 4 │ Wk 5 │ Wk 6 │ Wk 7 │ Wk 8 │ Wk 9 │ Wk10 │

├──────┴──────┴──────┴──────┴──────┴──────┴──────┴──────┴──────┴──────┤

│ ▓▓▓▓▓▓▓▓▓▓▓▓                                          Planning     │

│       ▓▓▓▓▓▓▓▓▓▓▓▓                                    Setup        │

│             ▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓                        Auth         │

│                         ▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓            Student      │

│                                       ▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓▓Admin        │

│                                                 ▓▓▓▓▓▓Dashboard    │

│                                                       ▓▓▓▓▓▓Testing │

│                                                       ▓▓▓▓▓▓Deploy │

└─────────────────────────────────────────────────────────────────────┘

```

12.2 Detailed Phase Breakdown

PHASE 1: Planning & Setup (Weeks 1-2)

```

┌─────────────────────────────────────────────────────────────────────┐

│ PHASE 1: PLANNING & SETUP                                           │

│ Duration: 2 Weeks | Hours: 40                                       │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│ Week 1: Requirements & Design                                       │

│ ├── Day 1-2: Stakeholder meetings                                   │

│ ├── Day 3-4: Requirement documentation                              │

│ └── Day 5:   UI/UX wireframes                                       │

│                                                                     │

│ Week 2: Technical Setup                                             │

│ ├── Day 1:   Project structure setup                                │

│ ├── Day 2:   Database design finalization                           │

│ ├── Day 3:   Development environment setup                          │

│ ├── Day 4:   Git repository & CI/CD setup                           │

│ └── Day 5:   Initial deployment pipeline                            │

│                                                                     │

│ Deliverables:                                                       │

│ ☐ Requirements Document (SRS)                                       │

│ ☐ Database Schema                                                   │

│ ☐ Wireframes/Mockups                                                │

│ ☐ Project Repository                                                │

│ ☐ Development Environment                                           │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

```

PHASE 2: Authentication System (Weeks 3-4)

```

┌─────────────────────────────────────────────────────────────────────┐

│ PHASE 2: AUTHENTICATION SYSTEM                                      │

│ Duration: 2 Weeks | Hours: 40                                       │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│ Week 3: Backend Authentication                                      │

│ ├── Day 1:   User model & database migrations                       │

│ ├── Day 2:   Registration API endpoint                              │

│ ├── Day 3:   Login API with JWT                                     │

│ ├── Day 4:   Password reset functionality                           │

│ └── Day 5:   API testing & documentation                            │

│                                                                     │

│ Week 4: Frontend Authentication                                     │

│ ├── Day 1:   React project setup with Tailwind                      │

│ ├── Day 2:   Login page UI                                          │

│ ├── Day 3:   Registration page UI                                   │

│ ├── Day 4:   Auth context & protected routes                        │

│ └── Day 5:   Integration testing                                    │

│                                                                     │

│ Deliverables:                                                       │

│ ☐ Working registration system                                       │

│ ☐ Working login system                                              │

│ ☐ JWT authentication                                                │

│ ☐ Password reset flow                                               │

│ ☐ Protected routes                                                  │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

```

PHASE 3: Student Portal (Weeks 5-6)

```

┌─────────────────────────────────────────────────────────────────────┐

│ PHASE 3: STUDENT PORTAL                                             │

│ Duration: 2 Weeks | Hours: 40                                       │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│ Week 5: Complaint Submission                                        │

│ ├── Day 1:   Complaint & Response models                            │

│ ├── Day 2:   Submit complaint API                                   │

│ ├── Day 3:   Submit complaint UI form                               │

│ ├── Day 4:   File upload functionality                              │

│ └── Day 5:   Ticket number generation                               │

│                                                                     │

│ Week 6: Complaint Tracking                                          │

│ ├── Day 1:   List complaints API & UI                               │

│ ├── Day 2:   Complaint detail page                                  │

│ ├── Day 3:   Response/comment system                                │

│ ├── Day 4:   Student dashboard                                      │

│ └── Day 5:   Testing & bug fixes                                    │

│                                                                     │

│ Deliverables:                                                       │

│ ☐ Complaint submission form                                         │

│ ☐ File attachment support                                           │

│ ☐ Complaint list with filters                                       │

│ ☐ Complaint detail view                                             │

│ ☐ Response/messaging system                                         │

│ ☐ Student dashboard                                                 │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

```

PHASE 4: Admin Portal (Weeks 7-8)

```

┌─────────────────────────────────────────────────────────────────────┐

│ PHASE 4: ADMIN PORTAL                                               │

│ Duration: 2 Weeks | Hours: 40                                       │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│ Week 7: Complaint Management                                        │

│ ├── Day 1:   Admin routes & permissions                             │

│ ├── Day 2:   View all complaints API                                │

│ ├── Day 3:   Admin complaint list UI                                │

│ ├── Day 4:   Update status & priority                               │

│ └── Day 5:   Assign complaints                                      │

│                                                                     │

│ Week 8: User Management & Admin Features                            │

│ ├── Day 1:   User management APIs                                   │

│ ├── Day 2:   User management UI                                     │

│ ├── Day 3:   Admin response to complaints                           │

│ ├── Day 4:   Internal notes feature                                 │

│ └── Day 5:   Testing & refinements                                  │

│                                                                     │

│ Deliverables:                                                       │

│ ☐ Admin complaint management                                        │

│ ☐ Status update functionality                                       │

│ ☐ Complaint assignment                                              │

│ ☐ User management (Super Admin)                                     │

│ ☐ Admin response system                                             │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

```

PHASE 5: Dashboard & Reports (Week 9)

```

┌─────────────────────────────────────────────────────────────────────┐

│ PHASE 5: DASHBOARD & REPORTS                                        │

│ Duration: 1 Week | Hours: 20                                        │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│ Week 9: Analytics & Reporting                                       │

│ ├── Day 1:   Dashboard statistics APIs                              │

│ ├── Day 2:   Charts implementation                                  │

│ ├── Day 3:   Admin dashboard UI                                     │

│ ├── Day 4:   Report generation                                      │

│ └── Day 5:   Export functionality (PDF/Excel)                       │

│                                                                     │

│ Deliverables:                                                       │

│ ☐ Statistics API endpoints                                          │

│ ☐ Interactive charts                                                │

│ ☐ Admin dashboard                                                   │

│ ☐ Report generation                                                 │

│ ☐ Data export                                                       │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

```

PHASE 6: Testing & Deployment (Week 10)

```

┌─────────────────────────────────────────────────────────────────────┐

│ PHASE 6: TESTING & DEPLOYMENT                                       │

│ Duration: 1 Week | Hours: 20                                        │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│ Week 10: QA & Launch                                                │

│ ├── Day 1:   Unit & integration testing                             │

│ ├── Day 2:   User acceptance testing                                │

│ ├── Day 3:   Bug fixes & optimizations                              │

│ ├── Day 4:   Production deployment                                  │

│ └── Day 5:   Documentation & handover                               │

│                                                                     │

│ Deliverables:                                                       │

│ ☐ Test reports                                                      │

│ ☐ Bug-free application                                              │

│ ☐ Production deployment                                             │

│ ☐ User documentation                                                │

│ ☐ Technical documentation                                           │

│ ☐ Training materials                                                │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

```

---

13. RISK ASSESSMENT

13.1 Risk Matrix

```

┌─────────────────────────────────────────────────────────────────────┐

│                        RISK MATRIX                                  │

└─────────────────────────────────────────────────────────────────────┘

IMPACT

Low      Medium     High

┌────────┬────────┬────────┐

High │   M    │   H    │   H    │

├────────┼────────┼────────┤

PROB Medium│   L    │   M    │   H    │

├────────┼────────┼────────┤

Low  │   L    │   L    │   M    │

└────────┴────────┴────────┘

L = Low Risk | M = Medium Risk | H = High Risk

```

13.2 Identified Risks

| ID | Risk | Probability | Impact | Level | Mitigation Strategy |

|----|------|-------------|--------|-------|---------------------|

| R1 | Scope creep | High | Medium | HIGH | Clear requirements sign-off, change control process |

| R2 | Delayed feedback from client | Medium | High | HIGH | Regular check-ins, set response deadlines |

| R3 | Technical challenges | Medium | Medium | MEDIUM | Research ahead, have backup solutions |

| R4 | Security vulnerabilities | Low | High | MEDIUM | Security testing, follow best practices |

| R5 | Performance issues | Low | Medium | LOW | Load testing, optimization |

| R6 | Integration issues | Medium | Medium | MEDIUM | Early API testing, clear documentation |

| R7 | Resource unavailability | Low | High | MEDIUM | Backup resources, documentation |

| R8 | Data loss | Low | High | MEDIUM | Regular backups, version control |

13.3 Risk Response Plan

```

┌─────────────────────────────────────────────────────────────────────┐

│                    RISK RESPONSE PLAN                               │

└─────────────────────────────────────────────────────────────────────┘

RISK R1: SCOPE CREEP

├── Prevention:

│   ├── Detailed requirements document

│   ├── Client sign-off on requirements

│   └── Clear change request process

├── Response:

│   ├── Evaluate impact on timeline/budget

│   ├── Document all changes

│   └── Adjust timeline if approved

└── Contingency:

└── 10% buffer in timeline

RISK R2: DELAYED CLIENT FEEDBACK

├── Prevention:

│   ├── Weekly status meetings

│   ├── Clear communication channels

│   └── Set response deadlines

├── Response:

│   ├── Follow up via multiple channels

│   ├── Proceed with assumptions (documented)

│   └── Escalate if necessary

└── Contingency:

└── Build non-blocking features first

RISK R4: SECURITY VULNERABILITIES

├── Prevention:

│   ├── Security best practices

│   ├── Input validation

│   ├── OWASP guidelines

│   └── Code review

├── Response:

│   ├── Immediate patching

│   ├── Security audit

│   └── Penetration testing

└── Contingency:

└── Security incident response plan

```

---

14. TESTING PLAN

14.1 Testing Strategy

```

┌─────────────────────────────────────────────────────────────────────┐

│                      TESTING PYRAMID                                │

└─────────────────────────────────────────────────────────────────────┘

┌───────────┐

│   E2E     │  ← Few, Slow, Expensive

│  Tests    │

┌┴───────────┴┐

│ Integration │

│   Tests     │

┌┴─────────────┴┐

│    Unit       │

│    Tests      │  ← Many, Fast, Cheap

└───────────────┘

```

14.2 Test Categories

Unit Testing

```

┌─────────────────────────────────────────────────────────────────────┐

│ UNIT TESTS                                                          │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│ Backend (Python/pytest):                                            │

│ ├── Model tests                                                     │

│ │   ├── User model validation                                       │

│ │   ├── Complaint model validation                                  │

│ │   └── Response model validation                                   │

│ ├── Utility function tests                                          │

│ │   ├── Password hashing                                            │

│ │   ├── Token generation                                            │

│ │   └── Ticket number generation                                    │

│ └── Coverage target: 80%+                                           │

│                                                                     │

│ Frontend (Jest/React Testing Library):                              │

│ ├── Component tests                                                 │

│ │   ├── Form components                                             │

│ │   ├── Button components                                           │

│ │   └── Card components                                             │

│ ├── Hook tests                                                      │

│ │   ├── useAuth hook                                                │

│ │   └── useComplaints hook                                          │

│ └── Coverage target: 70%+                                           │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

```

Integration Testing

```

┌─────────────────────────────────────────────────────────────────────┐

│ INTEGRATION TESTS                                                   │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│ API Integration Tests:                                              │

│ ├── Authentication flow                                             │

│ │   ├── Register → Login → Get Profile                              │

│ │   └── Login → Refresh Token → Access Protected Route              │

│ ├── Complaint flow                                                  │

│ │   ├── Create → Read → Update → Delete                             │

│ │   └── Create → Add Response → Update Status                       │

│ └── Admin flow                                                      │

│     ├── View All → Assign → Respond → Close                         │

│     └── Create User → Update → Deactivate                           │

│                                                                     │

│ Database Integration:                                               │

│ ├── CRUD operations                                                 │

│ ├── Foreign key constraints                                         │

│ └── Transaction handling                                            │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

```

End-to-End Testing

```

┌─────────────────────────────────────────────────────────────────────┐

│ E2E TESTS (Cypress/Playwright)                                      │

├─────────────────────────────────────────────────────────────────────┤

│                                                                     │

│ Student Scenarios:                                                  │

│ ├── Complete registration flow                                      │

│ ├── Submit complaint with attachments                               │

│ ├── Track complaint status                                          │

│ └── Add response to complaint                                       │

│                                                                     │

│ Admin Scenarios:                                                    │

│ ├── Login and view dashboard                                        │

│ ├── Filter and search complaints                                    │

│ ├── Update complaint status                                         │

│ ├── Assign complaint to staff                                       │

│ └── Generate and export report                                      │

│                                                                     │

└─────────────────────────────────────────────────────────────────────┘

```

14.3 Test Cases (Sample)

| TC ID | Module | Test Case | Expected Result | Priority |

|-------|--------|-----------|-----------------|----------|

| TC001 | Auth | Register with valid data | Account created, JWT returned | High |

| TC002 | Auth | Register with existing email | Error: Email already exists | High |

| TC003 | Auth | Login with valid credentials | JWT token returned | High |

| TC004 | Auth | Login with wrong password | Error: Invalid credentials | High |

| TC005 | Complaint | Submit complaint with all fields | Ticket number generated | High |

| TC006 | Complaint | Submit without required fields | Validation errors | High |

| TC007 | Complaint | View own complaints | List of user's complaints | High |

| TC008 | Complaint | View others' complaints | Access denied error | High |

| TC009 | Admin | Update complaint status | Status updated, notification sent | High |

| TC010 | Admin | View dashboard statistics | Accurate counts displayed | Medium |

---

15. DEPLOYMENT PLAN

15.1 Deployment Architecture

```

┌─────────────────────────────────────────────────────────────────────┐

│                    DEPLOYMENT ARCHITECTURE                          │

└─────────────────────────────────────────────────────────────────────┘

┌─────────────────┐

│    INTERNET     │

└────────┬────────┘

│

┌────────▼────────┐

│   CLOUDFLARE    │

│   (CDN + DNS)   │

└────────┬────────┘

│

┌────────▼────────┐

│     NGINX       │

│ (Load Balancer) │

└────────┬────────┘

│

┌───────────────────┼───────────────────┐

│                   │                   │

┌────────▼────────┐ ┌────────▼────────┐ ┌────────▼────────┐

│   FRONTEND      │ │   BACKEND       │ │   BACKEND       │

│   (Static)      │ │   Server 1      │ │   Server 2      │

│   React Build   │ │   Flask API     │ │   Flask API     │

└─────────────────┘ └────────┬────────┘ └────────┬────────┘

│                   │

└─────────┬─────────┘

│

┌──────────────────┼──────────────────┐

│                  │                  │

┌────────▼────────┐ ┌───────▼───────┐ ┌────────▼────────┐

│   POSTGRESQL    │ │    REDIS      │ │   FILE STORAGE  │

│   Database      │ │    Cache      │ │   (S3/Spaces)   │

└─────────────────┘ └───────────────┘ └─────────────────┘

```

15.2 Deployment Environments

```

┌─────────────────────────────────────────────────────────────────────┐

│                    ENVIRONMENT STRATEGY                             │

└─────────────────────────────────────────────────────────────────────┘

┌─────────────────┬─────────────────┬─────────────────┐

│   DEVELOPMENT   │     STAGING     │   PRODUCTION    │

├─────────────────┼─────────────────┼─────────────────┤

│                 │                 │                 │

│ Purpose:        │ Purpose:        │ Purpose:        │

│ Local dev &     │ Testing &       │ Live users      │

│ feature work    │ client review   │                 │

│                 │                 │                 │

│ Database:       │ Database:       │ Database:       │

│ SQLite          │ PostgreSQL      │ PostgreSQL      │

│                 │                 │ (Managed)       │

│                 │                 │                 │

│ URL:            │ URL:            │ URL:            │

│ localhost:3000  │ staging.app.com │ app.com         │

│ localhost:5000  │                 │                 │

│                 │                 │                 │

│ Auto Deploy:    │ Auto Deploy:    │ Auto Deploy:    │

│ No              │ On PR merge     │ Manual trigger  │

│                 │ to develop      │ from staging    │

│                 │                 │                 │

└─────────────────┴─────────────────┴─────────────────┘

```

15.3 Deployment Checklist

```

┌─────────────────────────────────────────────────────────────────────┐

│                    DEPLOYMENT CHECKLIST                             │

└─────────────────────────────────────────────────────────────────────┘

PRE-DEPLOYMENT:

☐ All tests passing

☐ Code review completed

☐ Environment variables configured

☐ Database migrations ready

☐ SSL certificates valid

☐ Backup of current production

☐ Rollback plan documented

DEPLOYMENT:

☐ Enable maintenance mode

☐ Run database migrations

☐ Deploy backend code

☐ Deploy frontend build

☐ Clear caches

☐ Verify health checks

☐ Disable maintenance mode

POST-DEPLOYMENT:

☐ Smoke tests passed

☐ Monitor error logs

☐ Monitor performance metrics

☐ Verify email notifications

☐ User acceptance verification

☐ Update documentation

```

---

16. DELIVERABLES

16.1 Deliverables List

```

┌─────────────────────────────────────────────────────────────────────┐

│                      PROJECT DELIVERABLES                           │

└─────────────────────────────────────────────────────────────────────┘

DOCUMENTATION DELIVERABLES:

├── D1: Project Plan Document (this document)

├── D2: Software Requirements Specification (SRS)

├── D3: Database Design Document

├── D4: API Documentation

├── D5: User Manual (Students)

├── D6: User Manual (Administrators)

├── D7: Technical Documentation

├── D8: Deployment Guide

└── D9: Training Materials

SOFTWARE DELIVERABLES:

├── D10: Backend API (Flask)

│    ├── Authentication module

│    ├── Student module

│    ├── Admin module

│    └── Dashboard module

├── D11: Frontend Application (React)

│    ├── Student portal

│    ├── Admin portal

│    └── Dashboard & reports

├── D12: Database (PostgreSQL)

│    ├── Schema

│    ├── Migrations

│    └── Seed data

└── D13: Test Suite

├── Unit tests

├── Integration tests

└── E2E tests

DEPLOYMENT DELIVERABLES:

├── D14: Deployed Application (Production)

├── D15: SSL Certificate

├── D16: Backup System

└── D17: Monitoring Setup

```

16.2 Deliverable Schedule

| Deliverable | Description | Due Date | Status |

|-------------|-------------|----------|--------|

| D1 | Project Plan | Week 1 | ☐ Pending |

| D2 | SRS Document | Week 2 | ☐ Pending |

| D3 | Database Design | Week 2 | ☐ Pending |

| D10.1 | Auth API | Week 4 | ☐ Pending |

| D11.1 | Auth UI | Week 4 | ☐ Pending |

| D10.2 | Student API | Week 6 | ☐ Pending |

| D11.2 | Student Portal | Week 6 | ☐ Pending |

| D10.3 | Admin API | Week 8 | ☐ Pending |

| D11.3 | Admin Portal | Week 8 | ☐ Pending |

| D10.4 | Dashboard API | Week 9 | ☐ Pending |

| D11.4 | Dashboard UI | Week 9 | ☐ Pending |

| D4 | API Documentation | Week 9 | ☐ Pending |

| D13 | Test Suite | Week 10 | ☐ Pending |

| D14 | Production Deploy | Week 10 | ☐ Pending |

| D5-D8 | Documentation | Week 10 | ☐ Pending |

---

17. BUDGET ESTIMATION

17.1 Cost Breakdown

```

┌─────────────────────────────────────────────────────────────────────┐

│                      BUDGET ESTIMATION                              │

└─────────────────────────────────────────────────────────────────────┘

DEVELOPMENT COSTS (One-Time):

┌─────────────────────────────────┬──────────┬──────────┬─────────────┐

│ Item                            │ Hours    │ Rate     │ Total       │

├─────────────────────────────────┼──────────┼──────────┼─────────────┤

│ Planning & Requirements         │ 40       │ $XX/hr   │ $XXX        │

│ Backend Development             │ 80       │ $XX/hr   │ $XXX        │

│ Frontend Development            │ 80       │ $XX/hr   │ $XXX        │

│ Testing & QA                    │ 20       │ $XX/hr   │ $XXX        │

│ Deployment & DevOps             │ 10       │ $XX/hr   │ $XXX        │

│ Documentation                   │ 10       │ $XX/hr   │ $XXX        │

├─────────────────────────────────┼──────────┼──────────┼─────────────┤

│ SUBTOTAL                        │ 240 hrs  │          │ $XXX        │

└─────────────────────────────────┴──────────┴──────────┴─────────────┘

INFRASTRUCTURE COSTS (Monthly):

┌─────────────────────────────────┬─────────────┐

│ Item                            │ Monthly     │

├─────────────────────────────────┼─────────────┤

│ Cloud Hosting (DigitalOcean)    │ $20-50      │

│ Database (Managed PostgreSQL)   │ $15-30      │

│ Domain Name                     │ $1-2        │

│ SSL Certificate (Let's Encrypt) │ Free        │

│ Email Service (SendGrid)        │ $0-20       │

│ File Storage (Spaces/S3)        │ $5-10       │

├─────────────────────────────────┼─────────────┤

│ MONTHLY TOTAL                   │ $41-112     │

└─────────────────────────────────┴─────────────┘

Note: Actual costs depend on negotiated rates and infrastructure choices

```

---

18. MAINTENANCE & SUPPORT

18.1 Post-Launch Support

```

┌─────────────────────────────────────────────────────────────────────┐

│                    MAINTENANCE & SUPPORT                            │

└─────────────────────────────────────────────────────────────────────┘

SUPPORT TIERS:

┌─────────────────┬───────────────────────────────────────────────────┐

│   Tier 1        │  Basic Support (Included)                         │

│   (30 days)     │  - Bug fixes                                      │

│                 │  - Minor adjustments                              │

│                 │  - Email support                                  │

├─────────────────┼───────────────────────────────────────────────────┤

│   Tier 2        │  Extended Support (Optional)                      │

│   (Monthly)     │  - All Tier 1 features                            │

│                 │  - New feature requests                           │

│                 │  - Priority response                              │

│                 │  - Monthly maintenance                            │

├─────────────────┼───────────────────────────────────────────────────┤

│   Tier 3        │  Premium Support (Optional)                       │

│   (Monthly)     │  - All Tier 2 features                            │

│                 │  - 24/7 monitoring                                │

│                 │  - Performance optimization                       │

│                 │  - Security updates                               │

│                 │  - Backup management                              │

└─────────────────┴───────────────────────────────────────────────────┘

MAINTENANCE ACTIVITIES:

├── Security patches and updates

├── Database optimization

├── Performance monitoring

├── Backup verification

├── Log analysis

└── User feedback implementation

```

---

19. APPROVAL & SIGN-OFF

```

┌─────────────────────────────────────────────────────────────────────┐

│                      PROJECT APPROVAL                               │

└─────────────────────────────────────────────────────────────────────┘

This document has been reviewed and approved by:

CLIENT/PROJECT SPONSOR:

Name: _______________________________

Signature: __________________________

Date: ______________________________

PROJECT MANAGER/DEVELOPER:

Name: _______________________________

Signature: __________________________

Date: ______________________________

TECHNICAL LEAD (if applicable):

Name: _______________________________

Signature: __________________________

Date: ______________________________

```

---

📎 APPENDICES

Appendix A: Glossary

| Term | Definition |

|------|------------|

| API | Application Programming Interface |

| JWT | JSON Web Token - authentication mechanism |

| CRUD | Create, Read, Update, Delete operations |

| ORM | Object-Relational Mapping |

| SPA | Single Page Application |

| MVP | Minimum Viable Product |

| UAT | User Acceptance Testing |

| SRS | Software Requirements Specification |

Appendix B: References

- Flask Documentation: https://flask.palletsprojects.com/

- React Documentation: https://react.dev/

- Tailwind CSS: https://tailwindcss.com/

- PostgreSQL: https://www.postgresql.org/docs/

---

What's Next?

Reply with one of these options:

1. "Start coding" - I'll continue with the actual code (where we left off)

2. "Explain [section]" - I'll explain any section in more detail

3. "Create wireframes" - I'll create UI wireframes/mockups

4. "Create SRS" - I'll create detailed Software Requirements Specification

Which would you like? 🚀